## Slide 1
SITUATION REPORT · PROJECT STATUS
Praxis Kretzschmar
Website Programme
Beriott GmbH — Dr. H. Macartney
Status of both practice websites measured against their User Requirements Specifications, verified against the code repository and the 17 May 2026 project handoff
Prepared by Beriott GmbH Reporting date: 20 May 2026

## Slide 2
EXECUTIVE SUMMARY
Where Both Projects Stand
Both websites are fully built and content-populated, running on Hostinger demo domains behind basic auth. Remaining work is concentrated in launch, legal-compliance and hardening tasks — not in the build itself. Percentages reflect the contractor's own milestone tables (URS §8 / handoff §8), independently cross-checked against the code repository.
Dr. Alexander Kretzschmar
~85%
complete
(self-reported)
Build, content & demo migration complete. Hero band reworked 17 May. Outstanding: real legal pages, font self-hosting, draft cleanup, production deploy.
Birgit Kretzschmar
~75%
complete
(self-reported)
Build complete. 14-May content/structure changes on Local only — not yet on demo. Awaiting reworked texts & photos; legal pages & 'Praxis' deletion pending.
Beriott GmbH | Dr. phil. Dr. rer. Nat. Henry Macartney · Situation Report, 20 May 2026
2
https://springgreen-viper-610216.hostingersite.com/
https://lightpink-wolf-142779.hostingersite.com/

## Slide 3
METHOD
How This Status Was Determined
You asked for a pragmatic read that trusts the URS milestone claims. It does — but every major claim was cross-checked against the actual code, so the figures are evidence-backed rather than simply transcribed.
Documents reviewed
Both URSs (Birgit / Alex, v1.0), and the authoritative self-contained project handoff dated 17 May 2026.
Code verified
praxis_base + alex_child theme zips inspected. Hero lines, prose CSS fix, Termine recurring repeater, Werdegang split — all confirmed present in code.
Scoring basis
Milestone tables taken at face value (your instruction). A discrepancy is flagged, not silently overridden.
One discrepancy found: praxis_base build-pipeline files (package.json / lock) absent from the supplied zip though the URS lists them — flagged on slide 7.
Beriott GmbH | Dr. phil. Dr. rer. Nat. Henry Macartney · Situation Report, 20 May 2026
3

## Slide 4
DR. ALEXANDER KRETZSCHMAR
Achieved vs. Remaining
Achieved
Child theme alex_child built, inherits praxis_base
All 9 pages live with real German content
Five-band landing page; 6-card Leistungen grid
Hero reworked 17 May — new B/W images, 4-line headline (verified in code)
Contact Form 7 with DSGVO consent → Alex's email
Four-column footer via ACF Options Page
Logo + favicon; hamburger hidden on desktop
Migrated to Hostinger demo (14 May), basic-auth protected
Remaining
Real Impressum & Datenschutz — footer links 404; old-site source ready
Apply Alex's reworked page texts (delivered 15 May, not yet applied)
Hero-band re-arrangement per Alex's feedback
Self-host Google Fonts (DSGVO)
Cleanup Sample Page / Privacy Policy drafts
Tailwind md:hidden root-cause fix
SEO redirect map; caching + security plugins
Production provisioning + DNS cutover
Beriott GmbH | Dr. phil. Dr. rer. Nat. Henry Macartney · Situation Report, 20 May 2026
4

## Slide 5
BIRGIT KRETZSCHMAR
Achieved vs. Remaining
Achieved
All 7 primary pages + Leistungen overview + legal pages render
Runs directly on praxis_base (no child theme — by design)
Sticky cream nav; desktop + mobile navigation
Homepage 3-image gallery; Contact Form 7 + DSGVO
14 May: Über mich split, new Qualifikationen
14 May: Termine 'Regelmäßige Termine' recurring section (in code)
14 May: Tanz-/Paartherapie long-form content
Site-wide prose CSS fix (lists + links) — verified in code
Remaining
14-May changes NOT yet on demo — Local only; needs migration
Awaiting reworked texts + Canadian Rockies photos (end May)
Real Impressum & Datenschutz — placeholder; lawyer review
Delete unpublished 'Praxis' draft page
Self-host Google Fonts (DSGVO)
12 MB portrait + images not yet optimised
SEO redirect map (old slugs → /leistungen/…)
Production provisioning + DNS cutover
Beriott GmbH | Dr. phil. Dr. rer. Nat. Henry Macartney · Situation Report, 20 May 2026
5

## Slide 6
COMPLETION BREAKDOWN
By Workstream
Self-reported completion per workstream. Build and content are essentially done on both sites; the gap to launch is legal, compliance and deployment work.
Alex
Birgit
Theme / build
100%
100%
Content population
100%
80%
Demo deployment
100%
50%
Legal pages (Impressum/DS)
10%
10%
DSGVO hardening (fonts etc.)
15%
15%
SEO redirect map
0%
0%
Production launch
0%
0%
Weighted overall: Alex ~85% · Birgit ~75% (build-heavy weighting per handoff milestone tables)
Beriott GmbH | Dr. phil. Dr. rer. Nat. Henry Macartney · Situation Report, 20 May 2026
6

## Slide 7
GAPS & INPUTS NEEDED
What Could Slip — and What's Missing
KEY RISKS TO THE RETURN-FROM-VACATION DEADLINE
Legal pages on both sites are placeholder/404 and need lawyer review — a hard gate on go-live, partly outside Beriott's control.
Birgit's reworked texts & photos are an external dependency due end-May; content can't be finalised until they arrive.
Birgit's 14-May work is Local-only and uncommitted — single point of failure until pushed and migrated.
No caching/security plugins; DSGVO font self-hosting open on both sites.
TO TIGHTEN THIS REPORT FURTHER
Self-captured screenshots of both demo sites (I can't use the basic-auth credentials)
The Birgit-Termine editor URS (referenced but not supplied)
Draft Impressum/Datenschutz texts + lawyer status
Confirmation Birgit's content/photos have arrived
praxis_base build files (package.json) — absent from zip
Beriott GmbH | Dr. phil. Dr. rer. Nat. Henry Macartney · Situation Report, 20 May 2026
7

## Slide 8
BOTTOM LINE
Build Done — Launch Is the Final Step
Both sites are demo-ready and to be reviewed by the clients. Neither is blocked by engineering. The path to go-live runs through incomplete legal pages, DSGVO hardening, the redirect map, and production deployment — plus Birgit's pending content.
1
Commit & migrate
Push 14/17-May work; migrate Birgit's Local build to demo
2
Legal pages
Build real Impressum/Datenschutz both sites; route for lawyer review
3
DSGVO hardening
Self-host fonts; add caching + security; redirect map
4
Production
Provision Hostinger, AIO migrate, DNS cutover before return
Overall: Alex ~85%, Birgit ~75% complete (self-reported, code-verified). No engineering blockers; remaining work is launch-phase and solely client/lawyer-dependent.
8